Project Planning Phase - SB Works Freelance Platform

1. Introduction

Project planning document for SB Works Freelance Platform - a MERN-based marketplace connecting freelancers with clients.

2. Project Overview

Three-role freelance platform (Freelancer/Client/Admin) with real-time chat, bidding system, and project management.

3. Project Objectives

- Build functional freelance marketplace

- Secure role-based authentication

- Project posting and bidding system

- Real-time chat functionality

- Responsive dashboards for all roles

- Scalable architecture

4. Project Deliverables

- System design & architecture

- Database schemas

- React frontend with dashboards

- Node.js backend with APIs

- Real-time chat (Socket.io)

- Testing & deployment

- Documentation

5. Project Schedule (10-week timeline)

| Week | Phase | Key Tasks |
| --- | --- | --- |
| Week 1 | Planning & Design | Finalize requirements, create system architecture, design database schemas |
| Week 2 | Core Setup | Project initialization, authentication system, basic routing |
| Week 3 | User Management | Profile creation, role-based dashboards, skill management |
| Week 4 | Project System | Project posting, browsing, filtering, and basic CRUD operations |
| Week 5 | Bidding System | Bid submission, proposal management, application tracking |
| Week 6 | Real-time Features | Socket.io implementation, chat rooms, real-time notifications |
| Week 7 | Project Management | Project assignment, submission system, status tracking |
| Week 8 | Admin Features | Admin dashboard, user management, platform oversight |
| Week 9 | Testing & Refinement | Unit testing, integration testing, bug fixing, performance optimization |
| Week 10 | Deployment & Documentation | Deployment, documentation, final testing, handover |

6. Resource Planning

Human Resources

- 1 Full-stack Developer (MERN stack specialist)

- 1 UI/UX Designer (for responsive design and user experience)

- 1 QA Tester (for manual and automated testing)

- Project Owner (for requirement validation and sign-offs)

Software & Tools

- IDE: VS Code with React/Node extensions

- Version Control: Git with GitHub

- Frontend: React, React Router, Context API, Axios, Bootstrap

- Backend: Node.js, Express, Mongoose, Socket.io, JWT

- Database: MongoDB Atlas (cloud)

- Deployment: Vercel/Netlify (frontend), Render/Heroku (backend)

- Real-time: Socket.io for chat and notifications

- Testing: Jest, React Testing Library, Postman

- Design: Figma for UI mockups

7. Risk Assessment & Mitigation

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Real-time chat scalability | High | Medium | Implement room-based chat, optimize message storage |
| Payment system security | High | Medium | Implement milestone-based payments, use secure API patterns, add transaction logging |
| Database performance with chat | High | Medium | Optimize MongoDB queries, implement indexing, consider message archiving |
| Role-based access complexity | Medium | High | Implement clear middleware, thorough testing of all role combinations |
| Mobile responsiveness issues | Medium | High | Mobile-first design approach, extensive device testing |
| Scope creep with feature requests | Medium | High | Strict MVP definition, feature prioritization, regular scope reviews |
| User authentication vulnerabilities | High | Low | Implement JWT with secure storage, password hashing, session timeout |

8. Constraints

- Must use MERN stack with Socket.io for real-time features

- Limited to single developer initially (expand team if needed)

- Third-party payment gateway integration deferred to Phase 2

- Initial focus on core marketplace features (bidding, chat, project management)

- User verification system basic in MVP (enhanced in future)

9. Success Criteria

- All three user roles (Freelancer, Client, Admin) can complete their core workflows

- Real-time chat functions reliably with minimal latency

- Project bidding and assignment process works end-to-end

- Platform is responsive on mobile, tablet, and desktop

- No critical security vulnerabilities in authentication or data access

- Deployment successful with all features operational

- API response times under 2 seconds for 95% of requests

10. Communication & Progress Tracking

- Daily Standups: 15-minute syncs (or async updates in Slack)

- Weekly Reviews: Demo of completed features, planning for next week

- Version Control: GitHub with feature branches and pull requests

- Task Management: GitHub Projects or Trello board with columns:

  - Backlog

  - To Do

  - In Progress

  - Review

  - Done

- Documentation: All decisions documented in GitHub Wiki

11. Quality Assurance

- Unit Testing: Critical functions (authentication, bid calculations)

- Integration Testing: End-to-end user flows (post project → bid → assign → complete)

- Performance Testing: Load testing for chat and project browsing

- Security Testing: Authentication bypass attempts, SQL injection prevention

- Cross-browser Testing: Chrome, Firefox, Safari, Edge

- Mobile Testing: iOS and Android devices, various screen sizes

- User Acceptance Testing: Real user testing with all three roles

12. Deliverable Handoff

- Complete source code in GitHub repository with detailed README

- Live deployment URLs (frontend and backend)

- Database backup and restore instructions

- API documentation (Postman collection or Swagger)

- User manuals for each role type

- Deployment architecture diagram

- Future enhancement suggestions document

13. Next Steps (Immediate)

- Finalize Design: Complete system architecture and database design

- Repository Setup: Initialize GitHub repo with proper structure

- Environment Configuration: Set up development environment variables

- Component Library: Create reusable React component library

- API Specification: Define all REST endpoints and Socket.io events

- Sprint Planning: Break down Week 1 tasks into daily deliverables

- Testing Strategy: Define testing approach and tools

- Deployment Plan: Outline deployment strategy for each environment

14. Milestones & Checkpoints

| Milestone | Week | Deliverable |
| --- | --- | --- |
| M1: Authentication Complete | Week 2 | User registration/login with JWT for all roles |
| M2: Basic Dashboards | Week 3 | Role-specific dashboards with core navigation |
| M3: Project System Live | Week 4 | Project posting, browsing, and basic management |
| M4: Bidding Functional | Week 5 | Complete bid submission and management system |
| M5: Real-time Chat | Week 6 | Socket.io chat with room-based messaging |
| M6: Project Management | Week 7 | Project assignment, submission, and tracking |
| M7: Admin Dashboard | Week 8 | Complete admin oversight and management |
| M8: Testing Complete | Week 9 | All tests passing, no critical bugs |
| M9: Production Ready | Week 10 | Deployed, documented, and ready for users |

15. Budget & Cost Considerations

- Development Tools: Free tier available for all required tools

- Hosting: Free tiers for frontend/backend, MongoDB Atlas free cluster

- Domain: Optional custom domain ($10-15/year)

- SSL Certificate: Free through Let's Encrypt

- Future Costs: Scaling may require paid tiers for hosting and database